## Team Members
Sr. No. | Employee Name
1 | Rajesh V
2 | Sandeep K
3 | Gagana

## Rajesh V
Employee Name | Week Ending Date | Date Created | Task Id | Brief Task Description | Est.Start Date | Est.End Date | Actual Start Date | Actual End Date | Est. Time | Act. Time | Status % | Comments
Rajesh V | 2022-07-02 | 2022-06-25 | US #011 | Enable team on KSFC Project | 2022-06-27 | 2022-06-27 |  |  | 4 |  | 0%
Rajesh V | 2022-07-02 | 2022-06-25 | US #010.3 | Document Upload and file operation in Primary / Collateral Security Form | 2022-06-27 | 2022-06-27 |  |  | 4 |  | 0%
Rajesh V | 2022-07-02 | 2022-06-25 | US #010.6 | Unit and Integration testing in Primary / Collateral Security Form | 2022-06-27 | 2022-06-27 |  |  | 2 |  | 0%
Rajesh V | 2022-07-02 | 2022-06-25 | US #010.7 | Code Review and Code Refactor | 2022-06-28 | 2022-06-28 |  |  | 4 |  | 0%
Rajesh V | 2022-07-02 | 2022-06-25 | US #012.1 | Build User Interface form to capture the details of Hypothecation | 2022-06-28 | 2022-06-28 |  |  | 4 |  | 0%
Rajesh V | 2022-07-02 | 2022-06-25 | US #012.2 | Validate the form inputs entered by the user for Hypothecation Form | 2022-06-29 | 2022-06-29 |  |  | 4 |  | 0%
Rajesh V | 2022-07-02 | 2022-06-25 | US #012.3 | Document Upload and file operation in Hypothecation Form | 2022-06-29 | 2022-06-29 |  |  | 2 |  | 0%
Rajesh V | 2022-07-02 | 2022-06-25 | US #012.4 | Save the details into database once the validation are passed in Hypothecation Form | 2022-06-30 | 2022-06-30 |  |  | 4 |  | 0%
Rajesh V | 2022-07-02 | 2022-06-25 | US #012.5 | Build View , Edit and Delete functionality for Hypothecation Form | 2022-06-30 | 2022-07-01 |  |  | 8 |  | 0%
Rajesh V | 2022-07-02 | 2022-06-25 | US #012.6 | Unit and Integration testing in Hypothecation Form | 2022-07-01 | 2022-06-01 |  |  | 2 |  | 0%
Rajesh V | 2022-07-02 | 2022-06-25 | US #012.7 | Code Review and Code Refactor | 2022-06-02 | 2022-06-02 |  |  | 8 |  | 0%

## Sandeep
Employee Name | Week Ending Date | Date Created | Brief Task Description | Est.Start Date | Est.End Date | Actual Start Date | Actual End Date | Est. Time | Act. Time | Status % | Comments
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25
Sandeep | 2022-07-02 | 2022-06-25

## Gagana
Employee Name | Week Ending Date | Date Created | Brief Task Description | Est.Start Date | Est.End Date | Actual Start Date | Actual End Date | Est. Time | Act. Time | Status % | Comments
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25
Gagana | 2022-07-02 | 2022-06-25

## User Stories
Story # | User Stories | Est. (hrs) | Actual (hrs) | Status | Comments
US #000 | https://devpatel385029.invisionapp.com/prototype/KSFC-CSG-UC01-Legal-DocumentationScreens-cl4atbaxb00b03i01985d2glz/play/bcef0889 |  |  |  | Invision Link
US #001 | Environment setup for the KSFC Project | 1 | 1 | Done | Installed MySQL server and workbench
US #002 | Database Setup for the KSFC Project | 4 | 6 | Done | UTF_mb3 is an issue, needs to bring collation to utf_mb4
US #003 | Code setup and Analysis of the KSFC Project | 32 | 40 | Done
US #004 | Setup of source control repository in Bit bucket | 1 | 1 | Done
US #005 | Built a prototype CRUD operation in the code base as practice | 16 | 24 | Done
US #006 | Built a prototype View of IDM module - Primary and Secondary Security form | 16 |  | Done | Work on hold from 01-06-2022
US #007 | Built a view to display the list of Account Numbers of IDM module | 8 | 6 | Done
US #008 | Review and Redesign - Data Modeling on IDM module | 8 |  | Not Started
US #009 | Review frontend screen design of IDM module | 4 |  | Done
US #010 | Implementation of Primary Security and Secondary Security Form | 98 |  | In Progress
US #011 | Enabling the Team and get them started with Project | 8 |  | Not Started | Provide KT to team and help with development
US #012 | Implementation of Hypothecation Form | 32 |  | Not Started
US #013 | Implementation of Conditions Form | 32 |  | Not Started
US #014 | Implementation of Security Charge Details Form | 32 |  | Not Started
US #015 | Implementation of CERSAI Registration Form | 32 |  | Not Started
US #016 | Implementation of Legal Joint Finance Form | 32 |  | Not Started

## US #010
Story# | WBS | Description | Resource | Est. (hrs) | Actual (hrs) | Status | Comments
| 0 | Implementation of Primary Security and Secondary Security Form
US #010 | 1 | Build User Interface form to capture the details of the Primary and Secondary security | RV | 8 |  | Completed | Not Reviewed
US #010 | 2 | Validate the form inputs entered by the user | RV | 24 |  | Not Started
US #010 | 3 | Document Upload and file operation | RV | 16 |  | Not Started
US #010 | 4 | Save the details into database once the validation are passed | RV | 8 |  | InProgress | Changed the design to Pop Up form RB: Post save the action it is not redirecting to View page
US #010 | 5 | Build View , Edit and Delete functionality for the same above mentioned. | RV | 30 |  | InProgress | Need to build Pop up as the same above add security holder details
US #010 | 6 | Unit and Integration testing | RV | 4 |  | Not Started
US #010 | 7 | Review and Re-edits | RV | 8 |  | Not Started

## US #012
WBS | Description | Resource | Est. (hrs) | Actual (hrs) | Status | Comments
0 | Implementation of Hypothecation Form | RV
1 | Build User Interface form to capture the details of Hypothecation | RV | 4 |  | Not Started
2 | Validate the form inputs entered by the user | RV | 4 |  | Not Started
3 | Document Upload and file operation | RV | 2 |  | Not Started
4 | Save the details into database once the validation are passed | RV | 4 |  | Not Started
5 | Build View , Edit and Delete functionality for the same above mentioned. | RV | 8 |  | Not Started
6 | Unit and Integration testing | RV | 2 |  | Not Started
7 | Review and Re-Edits | RV | 8 |  | Not Started

## US #013
WBS | Description | Resource | Est. (hrs) | Actual (hrs) | Status | Comments
0 | Implementation of Conditions Form | GK
1 | Build User Interface form to capture the details of Conditions | GK | 4 |  | Not Started
2 | Validate the form inputs entered by the user | GK | 4 |  | Not Started
3 | Document Upload and file operation | GK | 2 |  | Not Started
4 | Save the details into database once the validation are passed | GK | 4 |  | Not Started
5 | Build View , Edit and Delete functionality for the same above mentioned. | GK | 8 |  | Not Started
6 | Unit and Integration testing | GK | 2 |  | Not Started
7 | Review and Re-Edits | GK | 8 |  | Not Started

## US #014
WBS | Description | Resource | Est. (hrs) | Actual (hrs) | Status | Comments
0 | Implementation of Security Charge Details Form | SK
1 | Build User Interface form to capture the details of Security Charge | SK | 4 |  | Not Started
2 | Validate the form inputs entered by the user | SK | 4 |  | Not Started
3 | Document Upload and file operation | SK | 2 |  | Not Started
4 | Save the details into database once the validation are passed | SK | 4 |  | Not Started
5 | Build View , Edit and Delete functionality for the same above mentioned. | SK | 8 |  | Not Started
6 | Unit and Integration testing | SK | 2 |  | Not Started
7 | Review and Re-Edits | SK | 8 |  | Not Started

## US #015
WBS | Description | Resource | Est. (hrs) | Actual (hrs) | Status | Comments
0 | Implementation of CERSAI Registration Form | RV
1 | Build User Interface form to capture the details of CERSAI Registration | RV | 4 |  | Not Started
2 | Validate the form inputs entered by the user | RV | 4 |  | Not Started
3 | Document Upload and file operation | RV | 2 |  | Not Started
4 | Save the details into database once the validation are passed | RV | 4 |  | Not Started
5 | Build View , Edit and Delete functionality for the same above mentioned. | RV | 8 |  | Not Started
6 | Unit and Integration testing | RV | 2 |  | Not Started
7 | Review and Re-Edits | RV | 8 |  | Not Started

## US #016
WBS | Description | Resource | Est. (hrs) | Actual (hrs) | Status | Comments
0 | Implementation of Legal Joint Finance Form | PK
1 | Build User Interface form to capture the details of Legal Joint Finance | PK | 4 |  | Not Started
2 | Validate the form inputs entered by the user | PK | 4 |  | Not Started
3 | Document Upload and file operation | PK | 2 |  | Not Started
4 | Save the details into database once the validation are passed | PK | 4 |  | Not Started
5 | Build View , Edit and Delete functionality for the same above mentioned. | PK | 8 |  | Not Started
6 | Unit and Integration testing | PK | 2 |  | Not Started
7 | Review and Re-Edits | PK | 8 |  | Not Started